## Summary
MBPay (FoxPro) → HRSys (.NET) Migration Map
Source: MBPay 2026.10.27.zip vs. HRReport repo, analyzed 2026-10-27.
Key finding: MBPay uses the same MySQL schemas (pay, pis/secpis) as HRSys, so this is feature porting, not data migration.
Module | Total | Has page | Partial | Missing | Verify | % Covered
System | 4 | 2 | 1 | 1 | 0 | 50%
Setup | 15 | 5 | 3 | 7 | 0 | 33.33%
Transaction | 13 | 4 | 3 | 6 | 0 | 30.77%
Reports | 46 | 20 | 6 | 20 | 0 | 43.48%
Account Configuration | 12 | 0 | 1 | 11 | 0 | 0%
Computation | 11 | 0 | 7 | 3 | 1 | 0%
Total | 101 | 31 | 21 | 48 | 1 | 30.69%
% Covered = rows with an HRSys page of the same name. The logic still has to be checked against FoxPro.
Phase 1 Findings by Severity | Total | Open
Critical | 3 | 1
High | 10 | 1
Medium | 7 | 0
Low | 2 | 1

## Feature Map
Module | FoxPro Menu / Function | FoxPro Form / Program | HRSys Equivalent | Status | Notes | Phase | Remarks
System | User Administration | FRMUSERMGR | _0506_UserManagement | Has page |  | 6
System | Change Password | FRMCHANGEPASS | login module | Partial | verify | 6
System | Log-out / Exit | LOGIN |  | Has page | web login | 6
System | Menu/access per user | pay.sysmenu, pay.useraccess, pay.acctaccess, pay.reportaccess |  | Missing |  | 6
Setup | Employee Rate | FRMEMPRATES | _0505_EmployeeRates | Has page |  | 2
Setup | Surety Bond Quota | FRMSBQUOTA |  | Missing |  | 2
Setup | SSS Table | FRMSSSTABLE | _0502_05_SSS | Has page |  | 2
Setup | Phil-Health Table | FRMPHICTABLE | _0502_06_PHIC | Has page |  | 2
Setup | Rate Over Basic Pay | FRMOTSETUP | _0504_00_PayrollgrpRates | Partial |  | 2
Setup | Salary Grade | salaryGrade |  | Missing |  | 2
Setup | Accounts Entry | FRMCHAROFACCT | _0502_ChartOfAccounts | Has page |  | 2
Setup | Account Mapping | AcctMapping |  | Missing |  | 2
Setup | Payroll Content | PAYCONTENT |  | Missing |  | 2
Setup | Deduction Order Setup | DEDUCTIONORDER |  | Missing |  | 2
Setup | Annual Tax Matrix | TAX_MATRIX | _0502_04_Tax | Has page |  | 2
Setup | Semi-Monthly Tax Matrix | FRMSEMIMONTHLYTAX | _0502_04_Tax | Partial | verify | 2
Setup | Account Code Entry | FRMACCTCODE | Chart of Accounts | Partial |  | 2
Setup | Minimum Rate Setup | FRMMINIMUMSETUP |  | Missing |  | 2
Setup | Status visible in payroll | emp_status_visible_to_pay |  | Missing |  | 2
Transaction | Earnings (per employee) | FRMEARNFINAL | _0602_EarningsEntry | Has page |  | 3
Transaction | Earnings (group) | FRMEARNINGS | _0602_12_GroupEarnings | Has page |  | 3
Transaction | Fixed Earnings / Grp Fixed Earnings | fixed_earnings, fixed_earnings_grp | _0602_11_FixedEarnings | Has page |  | 3
Transaction | 13th Mo Salary deduction setter | frm13thMonth_ded_Setter |  | Missing |  | 3
Transaction | Deductions (per employee) | FRMCANCELDEDN | _0604_DeductionEntry | Has page |  | 3
Transaction | Deductions (group) | FRMDEDUCTIONS | _0604_DeductionEntry | Partial |  | 3
Transaction | Partial Deductions | FRMPARTIALDED |  | Missing |  | 3
Transaction | Mandatory Deduction | ded_mandatory | DedmandatoryDataAccess | Partial |  | 3
Transaction | Hospitalization | ded_hospitalization |  | Missing |  | 3
Transaction | Payroll | PAYROLL4 (largest form, ~400KB) | _0605/_0606_PayrollProcess, DA605DataAccess | Partial | core — see Phase 1 | 3
Transaction | Payroll variants | payroll4_manual, _negativepay, _below500, _40_prcnt_salary, _calculator, _13mogenerator, retro_pay |  | Missing |  | 3
Transaction | Payroll (custom) | PAYROLLX |  | Missing |  | 3
Transaction | BIR Fields Mapping / Data Migration / Excel Upload | bir_fields_mapping, bir_empmas_migration, bir_excelUploading |  | Missing |  | 3
Reports | Deductions Summary | FRMDEDSUM | _1152_DeductionSummary | Has page |  | 5
Reports | Earnings Summary | FRMEARNSUM | _1102_EarningsSummary | Has page |  | 5
Reports | Deductions History | FRMDEDSUMEMP | _1154_DeductionHistory | Has page |  | 5
Reports | Earnings History | FRMEARNSUMEMP | _1103_EarningsHistory | Has page |  | 5
Reports | Monthly Deductions | FRMDEDMONTHLY | _1155_MonthlyDeductionSummary | Has page |  | 5
Reports | Monthly Earnings | FRMEARNMONTHLY | _1104_MonthlyEarningsReport | Has page |  | 5
Reports | Loan Summary | loans_management | _0603_LoansManagement | Partial |  | 5
Reports | Deduction Summary | rptdedsummary | _1153_ConsolidatedDeductionSummary | Partial | verify | 5
Reports | Retirement / Grp Retirement | rptretirement, rptretirement_grp | _1307, _1308 | Has page |  | 5
Reports | Bank Advice | FRMBANKADVISE | _1205_BankAdvise, _0703 | Has page |  | 5
Reports | Bank Charge | FRMBANKCHARGE | _1204_BankCharge, _0704 | Has page |  | 5
Reports | Bank Text File | FRMBANKTEXTFILE |  | Missing |  | 4
Reports | Payroll Register | FRMPAYROLLREGISTER | _1203_PayrollRegister, _0701 | Has page |  | 5
Reports | Payroll Register Gov | FRMPAYROLLREGISTER_GOV |  | Missing |  | 5
Reports | Payroll Register (Per Account) [+Gov] | FRMPAYROLLREGISTERPERACCT[_GOV] |  | Missing |  | 5
Reports | Payroll Register (Masterlist) | FRMREGISTERMASTER |  | Missing |  | 5
Reports | Payslip | FRMPS | _1202_Payslip, _0702 | Has page |  | 5
Reports | Payslip Gov / Per Employee [+Gov] | FRMPS_GOV, FRMPSPEREMPLOYEE[_GOV] |  | Missing |  | 5
Reports | Revised PS: Payroll Summary | payroll_register4 | _1206_PayrollSummaryPerGroup | Partial |  | 5
Reports | Revised PS: Register (2 Liner) | payroll_register4V2 |  | Missing |  | 5
Reports | Customized: Dressed Payslip / Register / Bank Advice / Text File | frmps_deduction_dressing, dressed_* |  | Missing |  | 5
Reports | 13th Month Detailed / Summary / Register / Bank Advice | FRM13THMONTHDETAILED, FRM13THMONTHSUMMARY, FRM132REGISTER, FRMBA13 | _1209, _1207, _1212, _1208 | Has page |  | 5
Reports | 13th Month per Client / per Employee variants (5) | FRM13DTLPERCLIENT, FRM13DTLPEREMP, FRM13SUMMARYCLIENT, FRM13SUMMARYEMP, FRM13REGISTER |  | Missing |  | 5
Reports | 13th Month Payslip | — | _1213_13thMonthPayslip | Has page | HRSys only | 5
Reports | Pag-IBIG Contribution Summary / Remittance | FRMPAGIBIGCONTRIBUTION, FRMPAGIBIGCONTREMIT | _1254_PagibigContribution | Has page |  | 5
Reports | Pag-IBIG Remittance (per client) | FRMPAGIBIGPERCLIENT |  | Missing |  | 4
Reports | Pag-IBIG / HDMF Loan Remittance | FRMPAGIBIGLOANREMIT, FRMHDMFLOANREMIT | _1255, _1256_CalamityLoanRemittance | Partial |  | 4
Reports | PhilHealth Contribution | FRMPHILHEALTHCONTRIBUTION | _1257_PHICContribution | Has page |  | 5
Reports | PhilHealth Remittance (Text File) | FRMPHICQUARTERLY |  | Missing |  | 4
Reports | PhilHealth ER2 | PHIC_ER2 |  | Missing |  | 4
Reports | PhilHealth Monthly [per client] | FRMPHMO, FRMPHMOPERCLIENT |  | Missing |  | 4
Reports | SSS R1-A | SSS_R1A |  | Missing |  | 4
Reports | SSS Loan Remittance | FRMSSSLOANREMITTANCE | _1253_SSSLoanRemittance | Has page |  | 5
Reports | SSS Contribution Remittance | FRMSSSCONTREMIT | _1252_SSSContribution | Has page |  | 5
Reports | SSS Contribution (Adjusted) / Per Client | FRMSSSCONTREMIT2, FRMSSSCONTREMITPERCLIENT |  | Missing |  | 4
Reports | SSS Payment Module | paymentsss |  | Missing |  | 4
Reports | Alphalist / Gov / Per Employee | FRMALPHALIST2, FRMALPHALIST_GOV, FRMALPHALISTSINGLE2 | _1302_TaxAnnualization | Partial |  | 4
Reports | Account Total | FRMACCOUNTTOTALS | _1309, _1313_AccountTotal | Has page |  | 5
Reports | BIR Form 1700 | FRMFORM1700 |  | Missing |  | 4
Reports | BIR Form 2316 | FRMFORM2316 |  | Missing |  | 4
Reports | Grand Total | FRMTOTALDED | _1312_GrandTotal | Has page |  | 5
Reports | Summary Per Client | FRMSUMPERCLIENT |  | Missing |  | 5
Reports | Withholding Tax Compliance Report | FRMWTCR | _1305_Compliance, _0705 | Partial | verify | 4
Reports | Balance Report (current / by date) | FRMBLANCEREP, FRMBLANCEREP2 |  | Missing |  | 5
Reports | COE (with compensation) | coe |  | Missing |  | 5
Reports | Quit Claims | FRMAR | _1304_QuitClaims | Has page |  | 5
Account Configuration | Emp. Status Included in Payroll | payroll_employee_status_inclusion |  | Missing |  | 2
Account Configuration | Meal Allowance | MEALALLOWANCECONFIG (+ fmealallowance.prg) |  | Missing |  | 2
Account Configuration | Uniform | UNIFORMCONFIG (+ funiform.prg) |  | Missing |  | 2
Account Configuration | Provision for Retirement | RETIREMENTCONFIG (+ fprovisionforretirement.prg) |  | Missing |  | 2
Account Configuration | OT Account Setup | ACCTOTCONFIG (+ fot.prg) | _0501_DutyRenderAcctMgt | Partial |  | 2
Account Configuration | Minimum Client Rate | MINRATESETUP |  | Missing |  | 2
Account Configuration | Deduction Dressing Mgt | deduction_dressing_mgt |  | Missing |  | 2
Account Configuration | ECOLA / CTPA / SEA Management | ecola_mgt, ctpamgt, seamgt (+ fecola, fctpa, fsea.prg) |  | Missing |  | 2
Account Configuration | Record Archiver | RecordArchiever, archieve_transaction |  | Missing |  | 2
Account Configuration | Tax Setter | tax_mapper (+ fclassifytax.prg) |  | Missing |  | 2
Account Configuration | Employee Account Exemption | deduction_exemption_management |  | Missing |  | 2
Account Configuration | 13th Month Settings | 13mosettings |  | Missing |  | 2
Computation | fcomputebasicpay | Basic pay | DA605DataAccess._01EmpByPayrollgrpRate etc. | Partial | compare | 1
Computation | fsssprem | SSS premium | DA605._01_PremSSS | Partial | compare | 1
Computation | fphicprem1 | PhilHealth premium | DA605._01_PremPHIC | Partial | compare | 1
Computation | fpagibigprem | Pag-IBIG premium | DA605._01_PremPagibig | Partial | compare | 1
Computation | ftax, fclassifytax | Withholding tax | DA605._01_Tax | Partial | compare | 1
Computation | calcloans | Loan amortization | DA605._01_Loans | Partial | compare | 1
Computation | minimumnet | Minimum net pay rule |  | Missing |  | 1
Computation | fot | Overtime |  | Missing |  | 1
Computation | fallowance, fmealallowance, funiform, fecola, fctpa, fsea, fincentiveleave, fcashbond, fprovisionforretirement | Allowances / special accounts |  | Missing |  | 1
Computation | loadgrpdedn, loadschedearn | Load scheduled earnings/deductions | _01_FE_to_Tmptbltran, _01_FEG_to_Tmptbltran | Partial |  | 1
Computation | fpayrollfooter, fzeroingflds | Payroll totals / reset |  | Verify | verify | 1

## Unmapped Tables
Schema | Table | HRSys Status | Remarks
pay | 13thmogrp | Not referenced in code
pay | 13thmosched | Not referenced in code
pay | 13thmosettings | Not referenced in code
pay | acctaccess | Not referenced in code
pay | acctconfig | Not referenced in code
pay | allowanceperday | Not referenced in code
pay | audit_payroll_lock | Not referenced in code
pay | coaconfig | Not referenced in code
pay | dedmandatory_trans | Not referenced in code
pay | deductiondressing | Not referenced in code
pay | empdedexemption | Not referenced in code
pay | empstatpisval | Not referenced in code
pay | hospitalizationacct | Not referenced in code
pay | hospitalizationdtl | Not referenced in code
pay | hospitalizationgrp | Not referenced in code
pay | hospitalizationhdr | Not referenced in code
pay | hospitalizationsavings | Not referenced in code
pay | hospitalizationstatus | Not referenced in code
pay | loansacctaccess | Not referenced in code
pay | loansref | Not referenced in code
pay | loansref_rep_access | Not referenced in code
pay | mealallowopt | Not referenced in code
pay | medtbl | Not referenced in code
pay | pisval_empdeploymenthist | Not referenced in code
pay | ratesamt | Not referenced in code
pay | reportaccess | Not referenced in code
pay | reportlist | Not referenced in code
pay | retirementopt | Not referenced in code
pay | semimonthlytax | Not referenced in code
pay | ssstbl | Not referenced in code
pay | sysmenu | Not referenced in code
pay | tblatexemption | Not referenced in code
pay | tblbatch | Not referenced in code
pay | tblotherdedref | Not referenced in code
pay | tblotherdeductions | Not referenced in code
pay | tblotherearnings | Not referenced in code
pay | tbltranarchieved | Not referenced in code
pay | tbltrandeployment | Not referenced in code
pay | templock | Not referenced in code
pay | undeddeduction | Not referenced in code
pay | uniformopt | Not referenced in code
pay | useraccess | Not referenced in code
pay | tmp* (work tables) | Not referenced in code
pis | clbranch | Not referenced in code
pis | client_rate_settings | Not referenced in code
pis | client_rateatrail | Not referenced in code
pis | client_rateatrail_empmas | Not referenced in code
pis | empmasarchieved | Not referenced in code
pis | empstatforarchive | Not referenced in code
pis | userclientaccess | Not referenced in code

## Phases
Phase | Scope | Features | Missing | Partial / Verify
1 | Payroll computation parity: compare `payroll4.SCT` + `PROGS` with `DA605DataAccess`, run both on the same period, and fix differences. Add tests in `HRApiLibrary.Tests`. | 11 | 3 | 8
2 | Missing account configs that affect computation: OT, minimum net, ECOLA/CTPA/SEA, meal/uniform/retirement, deduction order, employee status inclusion, tax setter, 13th month settings. | 27 | 18 | 4
3 | Missing transactions: partial deductions, hospitalization, retro pay, payroll variants, BIR upload. | 13 | 6 | 3
4 | Government reports and files: SSS R1-A, PhilHealth ER2/text file, bank text file, Alphalist, BIR 1700/2316. | 13 | 10 | 3
5 | Remaining report variants: Gov / per client / per employee / dressed / 2-liner, COE, balance report. | 33 | 10 | 3
6 | Access control and archiving: sysmenu/useraccess equivalents, record archiver. | 4 | 1 | 1
Counts come from the Phase column (G) in Feature Map. Edit column G to re-plan.

## Phase 1 Findings
# | Area | FoxPro (payroll4) | HRSys (DA605) | Gap | Severity | Status | Remarks
1 | Payroll process UI | PAYROLL4 form runs the whole process | /03/0605 page has no content, /03/0606 is a placeholder; nothing in any branch calls DA605DataAccess | The .NET payroll process cannot be run by users | Critical | Open | Next: payroll process UI on /03/0605
2 | Basic pay | rateid 1 (monthly) = rate/2; 2 (daily) = rate × days; 3 (semi-monthly) = rate; employee rate 0 → client rate × days; monthly/semi-monthly paid even with 0 days | No rule in backend; Amount is whatever the UI sends to _03TmpTbltran | Basic pay rules missing | High | In progress | PayrollCalculator.BasicPay done and tested; wiring waits for the UI
3 | SSS basis | Bracket uses month-to-date earnings (already saved this month + current); EE = bracket EE − SSS already deducted this month | Bracket uses current TRN earnings only, then subtracts SSS already deducted this month | 2nd cutoff under-deducts SSS | High | Fixed | Month-to-date basis in _01_Premium
4 | SSS max | isMaxSSS = 1 → highest bracket regardless of earnings | Not supported | Missing | Medium | In progress | Calculator supports IsMaxSss; no column for it in HRSys yet
5 | SSS ER / ECC | Computes ER share and stores it (used by remittance reports) | EE only | ER share missing | Medium | In progress | Calculator returns ER; no table to store it yet (needed by remittance reports)
6 | SSS non-member | iswithSSS != 1 → skip | Earnings forced to 0 but still joined to matrix; a bracket starting at 0 would deduct minimum EE | Verify matrixSSS lowest bracket | Medium | Fixed | Non-members get 0
7 | PhilHealth formula | EE = fixed + (earnings × percent / 100) / 2 | EE = ee + earnings × percent / 100 (no ÷ 2) | Double the percentage part, unless matrixPHIC.percent is already halved — verify | High | Fixed | ÷ 2 applied. Verify that matrixPHIC.percent holds the total rate (e.g. 5), not the EE share
8 | PhilHealth basis | Month-to-date earnings, minus PHIC already deducted this month; skip if earnings = 0 | Current TRN earnings only | Same as #3 | High | Fixed | Month-to-date basis
9 | PhilHealth non-member | iswithPHIC != 1 → skip | if(wphic!=1, 0, …) - deducted → negative amount if there were earlier deductions | Wrong sign | Low | Fixed | Never negative
10 | Pag-IBIG SQL | n/a | left join pagibig p on t.t.Amount between … — MySQL error “Unknown column t.t.Amount” | D004 computation fails at runtime | Critical | Fixed | SQL replaced
11 | Pag-IBIG rules | iswithPagibig check; month-to-date earnings; EE − already deducted | No wPagibig check; current TRN only; if(deducted > earnings, 0, …) compares premium to earnings | Logic differs | High | Fixed | wPagibig check, month-to-date basis
12 | Tax basis | Taxable = current-period taxable earnings − SSS − PHIC − Pag-IBIG (current period) | (trn = @Trn or Status = 'P') and AcctNumber in coaTax → includes every posted record of the employee (all history); premiums not deducted | Tax heavily overstated | Critical | Fixed | Current TRN only, minus SSS/PHIC/Pag-IBIG
13 | Tax details | excess < 1 → 0; blank tax code → "S"; only istaxable = 1 | No floor on excess; uses deprecsettings.wTax | Minor differences | Medium | Fixed | Excess < 1 ignored, never negative
14 | Computation order | Premiums first, then tax (tax needs D002–D004) | Each account computed separately by caller; order not enforced | Tax can run before premiums | Medium | Fixed | _01_Tax computes missing premiums first
15 | Loans re-run | Skips a loan already deducted this period (same amount saved) | Check uses LEFT(trn,4) = LEFT(@Trn,6) (never true) and the result is unused | No duplicate protection | Medium | Fixed | Period check uses LEFT(trn,6); already-deducted loans skipped
16 | Loan closing | n/a | After posting: Status = 'I' where Amount < 1 — should be Balance < 1 | Paid-off loans stay Active | Medium | Fixed | Closes on Balance < 1
17 | Posting | Saves all rows, including negative ones (absent is a negative earning) | insert into TblTran … where Amount > 0 | Negative entries (absences, adjustments) are dropped | High | Fixed | Posts Amount != 0
18 | _01Acct_per_Trn | n/a | SQL has 3 values for 2 columns and missing parameters | Would fail if called (currently unused) | Low | Open | Unused method, left as is
19 | Overtime | Hourly = daily rate / 8 × OT rate × hours; non-daily uses salary-grade daily rate; ROT can use fixed amount from ratesamt | Not implemented | Missing | High | In progress | PayrollCalculator.Overtime done and tested
20 | Absent | −(hours × daily rate / 8), daily rate from salary grade or client rate | Not implemented | Missing | High | In progress | PayrollCalculator.Absent done and tested
21 | Minimum net / lock checks | Net < 1000 → zero out unlocked deductions and log to undeddeduction; block lock on negative net; warn if net 0–499 | Not implemented | Missing | High | In progress | ApplyMinimumNet and CheckNet done and tested
22 | Other earnings | ECOLA, CTPA, SEA, meal allowance, free uniform, incentive leave, provision for retirement, hospitalization, retro pay, 13th month | Not implemented (fixed earnings and mandatory deductions exist) | Missing | High | Open | Phase 2

## Phase 1 Decisions
# | Question | FoxPro actual behavior | Recommendation | Decision
D1 | Negative premiums | IIF(mpremee<1, mpremee=0, …) is a no-op in FoxPro, so negative premiums (refunds) are not clamped | Clamp to 0, which is what the code was meant to do | Approved (2026-10-27)
D2 | Minimum net: government deductions | The filter acct != 'D001' OR acct != 'D002' … is always true, so tax/SSS/PHIC/Pag-IBIG can also be zeroed (unless the account is locked) | Never zero D001–D004 | Approved (2026-10-27)
D3 | Minimum net threshold | Zeroing triggers below 1000; lock warning below 500 | Make both a setting | Approved (2026-10-27)
D4 | Tax method | Per-period lookup in semi-monthly table, no annualization | Keep for parity now; annualization is a separate feature (Alphalist/2316) | Approved (2026-10-27)
D5 | Minimum net: how many deductions to zero | LOOP in the SCAN continues instead of exiting, so every unlocked deduction is zeroed once net < 1000 | Zero from highest SortDed down only until net reaches 500 (implemented) | Implemented - please confirm
Fill in the yellow Decision column.